## Dashboard
ChurchPoa — Project Progress Tracker
Church Engagement & Management Mobile App — Implementation Progress Tracker
Project Start Date: | 2026-09-01 |  | Last Updated: | 2026-08-25
Total Tasks | Not Started | In Progress | Blocked | Complete | Overall % Complete
42 | 42 | 0 | 0 | 0 | 0
Progress by Sprint / Phase
Sprint / Phase | Avg % Complete | Status
Sprint 0 - Setup | 0 | Not Started
Sprint 1 - Membership & Content | 0 | Not Started
Sprint 2 - Events & Community | 0 | Not Started
Sprint 3 - Giving & Payments | 0 | Not Started
Sprint 4 - Live Stream & Notifications | 0 | Not Started
Sprint 5 - AI Assistant & Branding | 0 | Not Started
Sprint 6 - Hardening & QA | 0 | Not Started
Sprint 7 - UAT & Training | 0 | Not Started
Go-Live | 0 | Not Started

## Read Me
ChurchPoa — Progress Tracker
Church Engagement & Management Mobile App — Implementation Progress Tracker
How this workbook works
Read Me | You're on it. Explains the workbook and the colour coding used throughout.
Dashboard | Live summary: overall % complete, task counts by status, and a chart of progress by sprint. Everything here is a formula — nothing to type.
Sprint Schedule | One row per sprint/phase. Edit the blue 'Duration (weeks)' cell and the Project Start Date at the top; start/end dates and % complete recalculate automatically.
Tasks | The task list behind everything. Update Status, % Complete, Actual Start/End, and Notes as work progresses — everything else recalculates.
Colour legend
Blue text | A cell you're meant to edit (Status, % Complete, dates, Notes, Duration).
Black text | A formula. Leave these alone — they recalculate automatically from your inputs.
Green fill | Status = Complete
Yellow fill | Status = In Progress
Red fill | Status = Blocked
Grey fill | Status = Not Started
Tips
Updating status | Use the dropdown in the Status column on the Tasks sheet (Not Started / In Progress / Blocked / Complete).
Updating % complete | Enter a number from 0–100 in the % Complete column on the Tasks sheet.
Changing the schedule | Adjust the Project Start Date or a sprint's Duration (weeks) on the Sprint Schedule sheet — all dates shift automatically.
Adding a task | Insert a row in the Tasks sheet, fill in the Sprint (pick from the dropdown), Task, Owner, Priority, and Status. Planned dates will fill in automatically.

## Sprint Schedule
ChurchPoa — Sprint Schedule
Project Start Date: | 2026-09-01
Sprint / Phase | Duration (weeks) | Start Date | End Date | Tasks | Avg % Complete | Status
Sprint 0 - Setup | 1 | 2026-09-01 | 2026-09-07 | 5 | 0 | Not Started
Sprint 1 - Membership & Content | 2 | 2026-09-08 | 2026-09-21 | 5 | 0 | Not Started
Sprint 2 - Events & Community | 2 | 2026-09-22 | 2026-10-05 | 4 | 0 | Not Started
Sprint 3 - Giving & Payments | 3 | 2026-10-06 | 2026-10-26 | 6 | 0 | Not Started
Sprint 4 - Live Stream & Notifications | 2 | 2026-10-27 | 2026-11-09 | 4 | 0 | Not Started
Sprint 5 - AI Assistant & Branding | 2 | 2026-11-10 | 2026-11-23 | 4 | 0 | Not Started
Sprint 6 - Hardening & QA | 2 | 2026-11-24 | 2026-12-07 | 4 | 0 | Not Started
Sprint 7 - UAT & Training | 2 | 2026-12-08 | 2026-12-21 | 4 | 0 | Not Started
Go-Live | 2 | 2026-12-22 | 2027-01-04 | 6 | 0 | Not Started
Formulas:
Start Date = [End Date, row above]+1
End Date = [Start Date]+[Duration (weeks)]*7-1

## Tasks
Task ID | Sprint / Phase | Task | Owner | Priority | Status | % Complete | Planned Start | Planned End | Actual Start | Actual End | Notes
T001 | Sprint 0 - Setup | Provision development environment | DevOps Engineer | High | Not Started | 0 | 2026-09-01 | 2026-09-07
T002 | Sprint 0 - Setup | Provision staging environment | DevOps Engineer | High | Not Started | 0 | 2026-09-01 | 2026-09-07
T003 | Sprint 0 - Setup | Set up Git repository & branching strategy | Backend Developer | Medium | Not Started | 0 | 2026-09-01 | 2026-09-07
T004 | Sprint 0 - Setup | Configure CI/CD pipeline | DevOps Engineer | Medium | Not Started | 0 | 2026-09-01 | 2026-09-07
T005 | Sprint 0 - Setup | Finalize data model design (ERD sign-off) | Backend Developer | High | Not Started | 0 | 2026-09-01 | 2026-09-07
T006 | Sprint 1 - Membership & Content | Build registration, login & password reset | Backend Developer | High | Not Started | 0 | 2026-09-08 | 2026-09-21
T007 | Sprint 1 - Membership & Content | Build member profile management | Mobile Developer | Medium | Not Started | 0 | 2026-09-08 | 2026-09-21
T008 | Sprint 1 - Membership & Content | Build sermon management (admin) | Backend Developer | High | Not Started | 0 | 2026-09-08 | 2026-09-21
T009 | Sprint 1 - Membership & Content | Build home dashboard (verse of day, sermons, announcements) | Mobile Developer | High | Not Started | 0 | 2026-09-08 | 2026-09-21
T010 | Sprint 1 - Membership & Content | Integrate YouTube video playback | Mobile Developer | Medium | Not Started | 0 | 2026-09-08 | 2026-09-21
T011 | Sprint 2 - Events & Community | Build events calendar | Backend Developer | High | Not Started | 0 | 2026-09-22 | 2026-10-05
T012 | Sprint 2 - Events & Community | Build event registration & attendee tracking | Backend Developer | Medium | Not Started | 0 | 2026-09-22 | 2026-10-05
T013 | Sprint 2 - Events & Community | Build prayer wall | Mobile Developer | Medium | Not Started | 0 | 2026-09-22 | 2026-10-05
T014 | Sprint 2 - Events & Community | Build community groups & membership | Backend Developer | Medium | Not Started | 0 | 2026-09-22 | 2026-10-05
T015 | Sprint 3 - Giving & Payments | Integrate Stripe | Integration Engineer | High | Not Started | 0 | 2026-10-06 | 2026-10-26
T016 | Sprint 3 - Giving & Payments | Integrate PayPal | Integration Engineer | Medium | Not Started | 0 | 2026-10-06 | 2026-10-26
T017 | Sprint 3 - Giving & Payments | Integrate Flutterwave | Integration Engineer | Medium | Not Started | 0 | 2026-10-06 | 2026-10-26
T018 | Sprint 3 - Giving & Payments | Integrate Payhiive | Integration Engineer | Low | Not Started | 0 | 2026-10-06 | 2026-10-26
T019 | Sprint 3 - Giving & Payments | Integrate Mobile Money (M-Pesa) | Integration Engineer | High | Not Started | 0 | 2026-10-06 | 2026-10-26
T020 | Sprint 3 - Giving & Payments | Build donation reporting & reconciliation | Backend Developer | High | Not Started | 0 | 2026-10-06 | 2026-10-26
T021 | Sprint 4 - Live Stream & Notifications | Build live stream screen & YouTube Live integration | Mobile Developer | High | Not Started | 0 | 2026-10-27 | 2026-11-09
T022 | Sprint 4 - Live Stream & Notifications | Build countdown timer | Mobile Developer | Medium | Not Started | 0 | 2026-10-27 | 2026-11-09
T023 | Sprint 4 - Live Stream & Notifications | Set up Firebase project | Integration Engineer | High | Not Started | 0 | 2026-10-27 | 2026-11-09
T024 | Sprint 4 - Live Stream & Notifications | Implement push notifications (FCM) | Mobile Developer | High | Not Started | 0 | 2026-10-27 | 2026-11-09
T025 | Sprint 5 - AI Assistant & Branding | Integrate AI assistant API | Integration Engineer | Medium | Not Started | 0 | 2026-11-10 | 2026-11-23
T026 | Sprint 5 - AI Assistant & Branding | Configure AI assistant guardrails | Business Analyst | Medium | Not Started | 0 | 2026-11-10 | 2026-11-23
T027 | Sprint 5 - AI Assistant & Branding | Apply ChurchPoa branding | Mobile Developer | Medium | Not Started | 0 | 2026-11-10 | 2026-11-23
T028 | Sprint 5 - AI Assistant & Branding | Configure SMTP settings | Backend Developer | Low | Not Started | 0 | 2026-11-10 | 2026-11-23
T029 | Sprint 6 - Hardening & QA | Conduct security testing | QA Engineer | High | Not Started | 0 | 2026-11-24 | 2026-12-07
T030 | Sprint 6 - Hardening & QA | Conduct performance/load testing | QA Engineer | High | Not Started | 0 | 2026-11-24 | 2026-12-07
T031 | Sprint 6 - Hardening & QA | Fix critical & high defects | Backend Developer | High | Not Started | 0 | 2026-11-24 | 2026-12-07
T032 | Sprint 6 - Hardening & QA | Regression testing | QA Engineer | High | Not Started | 0 | 2026-11-24 | 2026-12-07
T033 | Sprint 7 - UAT & Training | Conduct UAT sessions with church staff | Business Analyst | High | Not Started | 0 | 2026-12-08 | 2026-12-21
T034 | Sprint 7 - UAT & Training | Collect & resolve UAT feedback | Backend Developer | High | Not Started | 0 | 2026-12-08 | 2026-12-21
T035 | Sprint 7 - UAT & Training | Conduct staff training | Business Analyst | Medium | Not Started | 0 | 2026-12-08 | 2026-12-21
T036 | Sprint 7 - UAT & Training | Obtain UAT sign-off | Project Manager | High | Not Started | 0 | 2026-12-08 | 2026-12-21
T037 | Go-Live | Submit app to Google Play Store | Mobile Developer | High | Not Started | 0 | 2026-12-22 | 2027-01-04
T038 | Go-Live | Submit app to Apple App Store | Mobile Developer | High | Not Started | 0 | 2026-12-22 | 2027-01-04
T039 | Go-Live | Deploy backend to production | DevOps Engineer | High | Not Started | 0 | 2026-12-22 | 2027-01-04
T040 | Go-Live | Perform production smoke testing | QA Engineer | High | Not Started | 0 | 2026-12-22 | 2027-01-04
T041 | Go-Live | Monitor hypercare period | DevOps Engineer | High | Not Started | 0 | 2026-12-22 | 2027-01-04
T042 | Go-Live | Go-live sign-off | Project Manager | High | Not Started | 0 | 2026-12-22 | 2027-01-04
Formulas:
Planned Start = INDEX('Sprint Schedule'!$C5:C13,MATCH([Sprint / Phase],'Sprint Schedule'!$A5:A13,0))
Planned End = INDEX('Sprint Schedule'!$D5:D13,MATCH([Sprint / Phase],'Sprint Schedule'!$A5:A13,0))